GENERAL LOCKS

Retail & Loyalty Module — Implementation Plan

ESP32 Multi-Tenant Attendance Platform

Prepared 2026-06-20  ·  Branch: Multi-Tenant-Architecture-Change

# Contents

(Right-click → Update Field, or press F9, to populate page numbers.)

# 1.  Overview & Approach

This plan takes the platform from its current state (the multi-tenant attendance system, Phases 1–5 complete) to an embedded retail & loyalty module serving a new shop-type tenant, GENERAL LOCKS (a dreadlock shop). The shop’s own staff attendance is already covered by the existing members/attendance tables; the new work is entirely about clients (customers), their visits, sales, and loyalty rewards.

The retail capability is embedded as a type-gated module on the existing Supabase project and Next.js dashboard — not a standalone system, and not a third member_type. It reuses auth, RBAC, RLS/ownership, theming, and the institution registry, while keeping retail data isolated in its own tables scoped by institution_id.

Phases are ordered by dependency and each is independently shippable and testable. Phase 8 (staff attendance hardware) runs in parallel with everything from Phase 1 onward — it is existing functionality with zero new code, but ESP32 procurement/enrollment has real lead time, so it should start early.

# 2.  Confirmed Decisions

These were validated with the owner and are baked into every phase below:

- Every buyer is identified: 
      transactions.client_id NOT NULL (no anonymous sales).

- One visit per client per day: 
      client_attendance UNIQUE(institution_id, client_id, date).

- Repeatable loyalty rewards: Punch-card “every N visits/spend”, not only one-time milestones. rewards_log is NOT unique on (client_id, reward_id); repeatable eligibility counts events since the last issuance. rewards carries repeatable + window_type.

- Issuance-only rewards: 
      rewards_log records issuance; no redemption/transaction linkage. “Automatic” rewards are auto-issued via a pg_cron job, not auto-applied to a sale.

- Stylists/cashiers use the dashboard: New cashier role: can create clients, log visits, record sales; cannot edit catalog, issue/configure rewards, or manage users/settings/devices.

- Embed, not standalone: GENERAL LOCKS = one new institutions row, type='shop' (third type after school/office); retail features are a type-gated module on the existing platform.

# 3.  Phase Summary

| # | Focus | Depends on |
| --- | --- | --- |
| 0 | Design lock — schema spec, role matrix, shop nav IA (spec only) | — |
| 1 | Platform foundation: shop type + cashier role | Phase 0 |
| 2 | Retail data layer — the 8 migrations | Phase 1 |
| 3 | Catalog management (Products & Services) | Phase 2 |
| 4 | Clients & visit tracking | Phase 2 |
| 5 | Point of Sale — record a sale | Phases 3, 4 |
| 6 | Rewards engine | Phase 5 |
| 7 | Reporting & analytics | Phases 5, 6 |
| 8 | Staff attendance setup (parallel, existing system) | Phase 1 (start early) |
| 9 | Onboarding, seeding & launch | Phases 3–7 |

# 4.  Phases

## Phase 0 — Design lock (spec only, no build)

Goal: Freeze the column-level schema, the role-access matrix, and the shop-type nav IA so the build phases don’t churn.

- Schema spec: Finalize exact columns / types / constraints for all 8 tables — price snapshot, soft-delete, NUMERIC(10,2), unique-visit-per-day, the exactly-one-of CHECK, and the rewards window_type / repeatable / payload fields.

- Role-access matrix: For super_admin / admin / cashier / platform_admin × every retail page and server action (who can read / create / edit / archive / issue).

- Shop nav IA: Decide exactly what a type='shop' tenant sees. Proposed: keep Attendance, Staff, Devices, Enrollment (shop staff still fingerprint clock-in), Accounts, Settings; hide Academic/Periods and Promotion (no terms); add a new “Shop” nav group: Clients, Catalog, Sales, Rewards, plus a shop-flavoured Overview.

- Vocabulary / locale: GHS currency formatting helper, timezone Africa/Accra, phone normalization rule (0XX ↔ +233).

Verify: No DB / code touched.

Exit: A one-page schema + access-matrix document, signed off.

## Phase 1 — Platform foundation: shop type + cashier role

Goal: The platform can represent a shop tenant and a POS-capable staff role, before any retail tables exist.

- DB: Drop/re-add institutions_type_check to include 'shop'; drop/re-add profiles_role_check to include 'cashier'; add cashier to the dormant authenticated RLS policies (auth_role() set) for future-proofing.

- Frontend: 
      InstitutionConfig.type union += 'shop' (lib/types.ts); UserRole += 'cashier' (lib/supabase/dal.ts); add cashier to ROLE_LABELS and the password/role hierarchy; extend buildNavItems type-gating in sidebar.tsx and the mobile nav components; add 'shop' to the type selector in the onboarding + settings forms.

- Decision baked in: 
      cashier slots below admin in the password/role hierarchy and is not cross-tenant.

Verify: Onboard a throwaway type='shop' institution; create a cashier account; confirm it logs in, sees the (still attendance-only) shop nav set, and is blocked from settings / devices.

Exit: Shop tenants and cashiers exist and are correctly gated — no retail features yet.

## Phase 2 — Retail data layer (the 8 migrations)

Goal: All retail tables live in cloud, with integrity enforced at the DB level. No UI.

- `clients`: name, phone (indexed), area_of_residence, institution_id, created_at.

- `products`: name, price NUMERIC(10,2), stock int, active, institution_id.

- `services`: name, price, active, institution_id.

- `client_attendance`: client_id, date, time, institution_id — UNIQUE(institution_id, client_id, date).

- `transactions`: client_id NOT NULL, client_attendance_id nullable, staff_id → members, total, created_at timestamptz, institution_id.

- `transaction_items`: transaction_id, product_id nullable, service_id nullable, quantity, unit_price, item_name — CHECK exactly one of product/service set.

- `rewards`: name, condition_type, condition_service_id?, condition_product_id?, condition_value, window_type, rolling_days?, repeatable, reward_kind + reward_product_id?/reward_service_id?/reward_value, auto, active, institution_id.

- `rewards_log`: client_id, reward_id, issued_at timestamptz, issued_by → auth user, trigger_source (manual|auto), value_snapshot, note, institution_id — NO unique(client_id, reward_id).

- Per table: institution_id + the “service role full access” RLS policy; FK on-delete matched to your existing convention (SET NULL where deletion should preserve history); indexes on (institution_id, …) lookup keys.

Verify: SQL only — insert sample rows; confirm unique-visit-per-day fires, the exactly-one CHECK fires, a catalog price change does not alter an existing transaction_items.unit_price, and ownsRecord resolves against a new table.

Exit: Schema is live and constraint-proven; dashboard still shows nothing new.

## Phase 3 — Catalog management (Products & Services)

Goal: Owner can manage what the shop sells.

- Pages: CRUD for products (name/price/stock) and services (name/price), under the new Shop nav group. Archive instead of delete (active flag).

- Guards: Server actions guarded by ownsRecord; super_admin/admin write, cashier read-only (needs to pick items at POS).

- Policy: Stock oversell decided here (recommend: allow negative, warn).

Verify: Preview — create/edit/archive a product and a service; archived items disappear from lists but stay in DB.

Exit: Catalog manageable; ready to be referenced by sales.

## Phase 4 — Clients & visit tracking

Goal: Client directory + the no-purchase visit log.

- Clients: CRUD (name/phone/area) with phone search as the primary lookup.

- Visits: “Log visit” action → upsert today’s client_attendance (idempotent on the unique key, so double-tap is safe). Per-client visit history.

- Access: 
      cashier can create clients and log visits; owner full.

Verify: Preview — log a visit twice in one day → still one row; phone search resolves a client.

Exit: Clients and visits captured independently of any sale.

## Phase 5 — Point of Sale (record a sale)

Goal: The core transaction flow ties clients, catalog, staff, and stock together.

- Sale flow: Pick client (required), auto-attach/create today’s visit, add line items (product or service + qty) snapshotting unit_price + item_name, assign stylist (staff_id), compute total, decrement product stock.

- Atomicity: Write transaction + transaction_items (+ visit upsert) atomically via a single server action / Postgres RPC.

- Lists: Sales list with date/client/staff filters + per-sale detail. Void policy decided here (recommend owner-only void flag with audit; no line editing).

- Access: 
      cashier creates; owner can void.

Verify: Preview — record a sale; confirm transaction + items + today’s visit exist and stock dropped; then raise a catalog price and confirm the past sale’s total is unchanged (snapshot proof).

Exit: Sales recorded end-to-end with immutable historical pricing.

## Phase 6 — Rewards engine

Goal: Loyalty rules, eligibility evaluation, manual + automatic issuance — issuance-only.

- Rules CRUD: Owner only: condition_type (service_count / product_count / visit_count / total_amount_spent), optional scoping id, threshold, window_type (lifetime / rolling_days / since_last_redemption), repeatable, reward payload, auto flag.

- Eligibility function: Postgres function/RPC: for a client + rule, count events in the window scoped by the optional id; for repeatables, count since the last rewards_log issuance for that (client, reward).

- Eligible-clients page: Owner sees who qualifies for what; manual issue → rewards_log row (trigger_source='manual', issued_by, value snapshot).

- Auto rewards: A pg_cron daily job (direct analog to mark-absent — needs pg_net, already a known dependency) evaluates auto=true rules across all clients and inserts rewards_log (trigger_source='auto'). No application to any sale.

- Audit: Rewards audit / history page.

Verify: Seed data so a punch-card rule (visit_count=10, repeatable, since_last_redemption) fires at visit 10, then again at 20; a one-time rule fires once; the cron issues auto rewards; manual issue logs issued_by correctly.

Exit: Loyalty issuance working, both manual and automatic.

## Phase 7 — Reporting & analytics

Goal: The reporting the owner actually runs the business on.

- Reports: Revenue per client; daily/weekly takings; popular products & services (by count and revenue); revenue by stylist; visit frequency; low-stock; rewards issued.

- Exports: CSV exports following the existing /api/attendance/export pattern.

- Overview: Shop-flavoured Overview at / (takings today, visits today, top service, low-stock) replacing the attendance stat cards for type='shop'.

Verify: Preview against Phase 5/6 sample data; spot-check totals against raw rows.

Exit: Owner has actionable revenue, popularity, and loyalty reporting.

## Phase 8 — Staff attendance setup (parallel track — start now)

Goal: The shop’s own staff clock in/out. No new code — existing members/attendance/devices/enrollment.

- Setup: Enroll stylists as members (member_type='staff'), provision ESP32 device(s), set staff_scan_mode (likely time_in_out), skip_weekends, timezone Africa/Accra.

- Timing: Independent of Phases 1–7 → begin procurement/enrollment immediately given hardware lead time.

Verify: Existing log-attendance / mark-absent flow already proven; confirm a staff clock-in lands in attendance.

Exit: Shop staff attendance live on the existing system.

## Phase 9 — Onboarding, seeding & launch

Goal: GENERAL LOCKS goes live.

- Provision: Create the real institution (type='shop', brand theme, labels, timezone); create owner super_admin + cashier accounts.

- Seed: Seed catalog (products/services + prices), import the existing client list, configure reward rules.

- Launch: Owner + cashier training; pilot/soft-launch with a reconciliation period.

- Docs: Update README phase table + docs; refresh the general-locks-retail memory if anything shifted in build.

Verify: Reconciliation period: cross-check recorded sales/visits against the shop’s own count.

Exit: Tenant live and reconciled.

# 5.  Cross-Cutting Concerns

These apply across every UI phase:

- Mobile nav parity: Every nav change touches sidebar.tsx + mobile-bottom-nav + mobile-header.

- Tenant ownership: Every server action that mutates a retail row calls ownsRecord — the service role bypasses RLS, so application code is the only tenant boundary.

- Realtime refresh: 
      /api/realtime-stream currently watches members/devices/periods/attendance; decide per phase whether to add clients/visits/transactions for live updates (optional, not blocking).

- Theming: Already works for shop tenants with no change.

# 6.  Deferred Decisions

Settle before the relevant phase; none block earlier work:

- Void/refund semantics: Transaction reversal handling (Phase 5).

- Per-line stylist attribution: Currently transaction-level; revisit only if commissions arrive.

- Stock movement ledger: Single stock counter for MVP (Phase 3); add a movements ledger later if inventory accuracy matters.

- Area of residence: Free-text vs. a controlled list for cleaner per-area reporting (Phase 4).